## Gantt Chart
Drought Monitoring in Africa
Module: ITRI 614
| Project Start: | 2024-04-23
| Project End: | 2024-10-01 |  | 2024-04-22 | [10 empty] | 2024-05-03 | [10 empty] | 2024-05-14 | [10 empty] | 2024-05-25 | [10 empty] | 2024-06-05 | [10 empty] | 2024-06-16 | [10 empty] | 2024-06-27 | [10 empty] | 2024-07-08 | [10 empty] | 2024-07-19 | [10 empty] | 2024-07-30 | [10 empty] | 2024-08-10 | [10 empty] | 2024-08-21 | [10 empty] | 2024-09-01 | [10 empty] | 2024-09-12 | [10 empty] | 2024-09-23
 | time axis 2024-04-22 to 2024-10-03
TASK | PROGRESS | START | END | time axis 2024-04-22 to 2024-10-03
Task 1 - Feasibility Study | 100% | 2024-04-23 | 2024-05-04
Task 1.1 - Executive Summary | 100% | 2024-04-30 | 2024-05-03
Task 1.2 - Description of Product/Service | 100% | 2024-04-23 | 2024-04-30
Task 1.3 - Technical Considerations | 100% | 2024-04-23 | 2024-04-30
Task 1.4 - Product/Service Marketplace | 100% | 2024-04-23 | 2024-04-30
Task 1.5 - Marketing Strategy | 100% | 2024-04-23 | 2024-04-30
Task 1.6 - Organisation/Staffing | 100% | 2024-04-23 | 2024-04-30
Task 1.7 - Schedule | 100% | 2024-04-23 | 2024-04-30
Task 1.8 - Financial Projections | 100% | 2024-04-23 | 2024-04-30
Task 1.9 - Findings and Recommendations | 100% | 2024-04-30 | 2024-05-03
Task 2 - IT Plan | 100% | 2024-05-06 | 2024-05-15
Task 2.1 - Overview | 100% | 2024-05-12 | 2024-05-14
Task 2.2 - Document Organisation | 100% | 2024-05-12 | 2024-05-14
Task 2.3 - Goals & Scope | 100% | 2024-05-06 | 2024-05-13
Task 2.4 - Technical Process | 100% | 2024-05-06 | 2024-05-11
Task 2.5 - Deliverables | 100% | 2024-05-06 | 2024-05-13
Task 2.6 - Risk Management | 100% | 2024-05-06 | 2024-05-13
Task 2.7 - Scheduling & Estimates | 100% | 2024-05-06 | 2024-05-13
Task 2.8 - Measurements and Metrics | 100% | 2024-05-06 | 2024-05-13
Task 2.9 - Appendix | 100% | 2024-05-06 | 2024-05-14
Task 3 - Business Case | 55.56% | 2024-05-15 | 2024-07-12
Task 3.1 - Executive Summary | 0% | 2024-05-15 | 2024-07-12
Task 3.2 - Mission Statement | 0% | 2024-05-15 | 2024-07-12
Task 3.3 - Product/Service | 100% | 2024-05-15 | 2024-07-09
Task 3.4 - Project Definition | 0% | 2024-05-15 | 2024-07-09
Task 3.5 - Project Organisation | 100% | 2024-05-15 | 2024-07-09
Task 3.6 - Market Assessment | 100% | 2024-05-15 | 2024-07-09
Task 3.7 - Marketing Strategy | 100% | 2024-05-15 | 2024-07-09
Task 3.8 - Financial Appraisal | 0% | 2024-05-15 | 2024-07-09
Task 3.9 - Risk Assessment | 100% | 2024-05-15 | 2024-07-09
Task 4 - ProtoType | 100% | 2024-05-20 | 2024-06-12
Task 4.1 - Database | 100% | 2024-05-20 | 2024-06-10
Task 4.2 - UI | 100% | 2024-05-20 | 2024-06-10
Task 4.3 - Graphs | 100% | 2024-05-20 | 2024-06-10
Task 5 - Final Product |  | 2024-06-14 | 2024-10-01

## WBS
Tabular Work Breakdown Structure
Task ID | Description | Assign | % complete | Start date | End date | Priority | Dependancy
1 | Feasibility Study |  | 100% | 2024-04-23 | 2024-05-04
1.1 | Executive Summary | Wilco | 100% | 2024-04-30 | 2024-05-03 | high | All the tasks
1.2 | Description of Product/Service | Rorisang | 100% | 2024-04-23 | 2024-04-30 | high
1.3 | Technical Considerations | Jevon | 100% | 2024-04-23 | 2024-04-30 | high
1.4 | Product/Service Marketplace | Melissa | 100% | 2024-04-23 | 2024-04-30 | high
1.5 | Marketing Strategy | Chriselda | 100% | 2024-04-23 | 2024-04-30 | high
1.6 | Organisation/Staffing | Sarah & Oratile | 100% | 2024-04-23 | 2024-04-30 | high
1.7 | Schedule | Sarah | 100% | 2024-04-23 | 2024-04-30 | high
1.8 | Financial Projections | Mduduzi | 100% | 2024-04-23 | 2024-04-30 | high
1.9 | Findings and Recommendations | Wilco & Rorisang | 100% | 2024-04-30 | 2024-05-03 | high
2 | IT Plan |  | 100% | 2024-05-06 | 2024-05-15
2.1 | Overview | Wilco | 100% | 2024-05-12 | 2024-05-14 | high | All the tasks
2.2 | Document Organisation | Wilco | 100% | 2024-05-12 | 2024-05-14 | high | All the tasks
2.3 | Goals & Scope | Chriselda | 100% | 2024-05-06 | 2024-05-13 | high
2.4 | Technical Process | Melissa | 100% | 2024-05-06 | 2024-05-11 | high
2.5 | Deliverables | Rorisang | 100% | 2024-05-06 | 2024-05-13 | high
2.6 | Risk Management | Jevon | 100% | 2024-05-06 | 2024-05-13 | high
2.7 | Scheduling & Estimates | Sarah & Oratile | 100% | 2024-05-06 | 2024-05-13 | high | 2.4
2.8 | Measurements and Metrics | Mduduzi | 100% | 2024-05-06 | 2024-05-13 | high
2.9 | Appendix | Rorisang | 100% | 2024-05-06 | 2024-05-14 | high | All the tasks
3 | Business Case |  | 55.56% | 2024-05-15 | 2024-07-12
3.1 | Executive Summary | Wilco | 0% | 2024-05-15 | 2024-07-12 | high | All the tasks
3.2 | Mission Statement | Oratile & Rorisang | 0% | 2024-05-15 | 2024-07-12 | high
3.3 | Product/Service | Rorisang | 100% | 2024-05-15 | 2024-07-09 | high
3.4 | Project Definition | Mduduzi | 0% | 2024-05-15 | 2024-07-09 | high
3.5 | Project Organisation | Sarah | 100% | 2024-05-15 | 2024-07-09 | high
3.6 | Market Assessment | Melissa | 100% | 2024-05-15 | 2024-07-09 | high
3.7 | Market Strategy | Chriselda | 100% | 2024-05-15 | 2024-07-09 | high
3.8 | Financial Appraisal | Sarah & Mduduzi | 0% | 2024-05-15 | 2024-07-09 | high
3.9 | Risk Assessment | Jevon | 100% | 2024-05-15 | 2024-07-09 | high
4 | Prototype |  | 100% | 2024-05-20 | 2024-06-12
4.1 | Database |  | 100% | 2024-05-20 | 2024-06-10 | High
4.2 | UI |  | 100% | 2024-05-20 | 2024-06-10 | High
4.3 | Graphs |  | 100% | 2024-05-20 | 2024-06-10 | High
5 | Final Product |  |  | 2024-06-14 | 2024-10-01

## Project Estimates
Project Estimates
Project Phase | Vendor/Contractor | Labour | Materials | Total | Notes
Ideation
Task 1 - Feasibility Plan | Internal | 2000 | 0 | 2000
Task 2 - IT Plan | Internal | 2000 | 0 | 2000
Task 3 - Business Case | Internal | 2000 | 0 | 2000
Subtotal |  | 6000 | 0 | 6000
Design
Task 4 - Prototype | Internal | 2000 | 0 | 2000
Task 5 - Final Product | Internal | 8000 | 2500 | 10500
Subtotal |  | 10000 | 2500 | 12500
Development
Task 4 - Prototype | Internal | 2500 | 0 | 2500
Task 5 - Final Product | Internal | 12500 | 0 | 12500
Subtotal |  | 15000 | 0 | 15000
Testing
Task 4 - Prototype | Internal | 1500 | 0 | 1500
Task 5 - Final Product | Internal | 3500 | 0 | 3500
Subtotal |  | 5000 | 0 | 5000
Pre-production
Task 4 - Prototype | Internal | 500 | 0 | 500
Task 5 - Final Product | Internal | 3500 | 0 | 3500
Subtotal |  | 4000 | 0 | 4000
Production
Task 5 - Final Product | Internal | 10000 | 10000 | 20000
Subtotal |  | 10000 | 10000 | 20000
Grand total |  | 50000 | 12500 | 62500