## Risk Management
Risk Name | Probability | Impact | Impact Value | Exposure | Classification | Owner | Mitigation Plan | Management Plan | Status
Data Accessibility and Quality | 40% | High | 10 | 400% | Quality |  | Regularly monitor data sources and implement data quality control measures. Establish backup plans for accessing alternative data sources if needed. | Have contingency plans in place for dealing with data inconsistencies or unavailability. Maintain open communication with stakeholders regarding data challenges. | Active
Stakeholder Engagement | 35% | High | 10 | 350% | Requirments |  | Establish clear channels of communication with stakeholders and the project team. Regularly update stakeholders on project progress and provide feedback. | Address stakeholder concerns promptly and adapt project plans as needed based on stakeholder input. | Active
Technology Integration Challenges | 30% | High | 10 | 300% | Quality |  | Conduct thorough compatibility testing during the integration phase. Develop contingency plans for addressing unforeseen integration issues. | Allocate additional resources to resolve integration challenges promptly. Keep stakeholders informed about any potential delays. | Active
Algorithm Complexity | 25% | Meduim | 5 | 125% | Quaity | Jevon Gounden | Conduct thorough algorithm design and testing to identify potential complexities early. Break down complex algorithms into manageable components. | Allocate sufficient time for algorithm development and debugging. | Active
Project Timeline Slippage | 25% | High | 10 | 250% | Scheduling |  | Develop a detailed project schedule potential delays. Regularly monitor progress against the schedule and adjust as needed. | Implement strategies to delegate critical tasks if the project falls behind schedule. Communicate revised timelines to stakeholders promptly. | Active
Resource Constraints | 20% | Meduim | 5 | 100% | Costs |  | Prioritise resource allocation based on project needs. Identify potential resource bottlenecks early and explore alternative solutions. | Regularly monitor resource utilisation and adjust allocation as necessary. Seek approval for additional resources if required. | Active
Communication Breakdown | 20% | High | 10 | 200% | Quality |  | Establish clear communication channels and protocols. Conduct regular team meetings and ensure documentation of important discussions. | Address communication issues promptly and transparently. Develop a culture of open communication within the team. | Active
Regulatory Compliance | 15% | Medium | 5 | 75% | Quality |  | Stay updated on relevant regulations and compliance requirements. | Quickly address any compliance issues that arise. | Active